Tentative Calendar of Activities for Technical Working Group

| Activities | Target Date |
| --- | --- |
| Goal 1: Seascapes WG |  |
| Write shop for Seascapes Model, Framework and M&E Indicators | April 5-7, 2016 |
| 2nd Regional Exchange on Seascapes | September 2016 |
| 3rd TWG Meeting | September 2016 |
| Submission of Seascapes Model, Framework, and M&E Indicators to SOM for endorsement | October 2016 |
| Seascape Working Group calls | Bi-monthly/Quarterly |
| Goal 2: EAFM WG |  |
| TWG call meetings | Bi-monthly |
| Coast Fish Workshop | June 2016 |
| Development of the EAFM Regional Level Indicators | October 2016 |
| 3rd Fisheries Forum | Second Quarter 2016 |
| 6Th EAFM TWG Meeting | July 2016 |
| Tuna Governance Workshop | 2016 |
| To incorporate learning into existing fisheries management plan (particularly in Sulu Celebes Sea, supported by NOAA) | 2016 |
| EAFM Knowledge exchange and training on fisheries prioritization exercise (SEAFDEC) | 2016 |
| Ministerial / Agency capacity building for each CT6 member country | 2016 |
| Draft the roadmap for regional advisory body for the LRFFT | 2016 |
| Goal 3: MPA WG |  |
| CTMPAS and Regional MPA Awards Mini Workshop | January 2016 |
| 6Th MPA REX | June 2016 |
| CTMPAS Nomination | March - October 2016 |
| Regional Recognition Awards | March - October 2016 |
| Goal 4: Climate Change Adaptation WG |  |
| Regular WG call meetings to keep everyone updated and to encourage sharing of ideas and practices | Bimonthly |
| Finalize the reporting format to be used to track CCA activities and to report progress to SOM as well as the reporting frequency | By end of Mar 2016 |
| Workshop on COE | April 2016 |
| Finalize the COE concept note, design, criteria and TOR which was drafted by WWF and initiate steps for the establishment of national COEs | By May 2016 |
| Develop an Executive Course on CCA based on the LEAP Guide for local government in collaboration with LGN | By end of 2016 |
| CCA REX, trainings, etc | ongoing |
| Goal 5: Threatened Species |  |
| Regular TSWG call conference | Bimonthly |
| Follow up documents from partners | January 2016 |
| Threatened Species Working Group Meeting | April 2016 |
| Preparation for the 1st TS REX | May-July |
| 1st Regional Exchange | August 2016 |
| Pre-SOM 12 working group meeting | November 2016 |